## Sheet1
Frequency (GHz) | Percentage | Cumulative percentage
0.4 | 3% | 3.1%
2.4 | 20% | 23.2%
3 | 3% | 26.3%
4 | 4% | 30.4%
4.3 | 3% | 33.5%
5.8 | 12% | 45.6%
7.3 | 1% | 46.7%
8.7 | 1% | 47.8%
10 | 4% | 51.9%
20 | 3% | 55%
24 | 28% | 83.1%
35 | 1% | 84.2%
60 | 4% | 88.3%
77 | 6% | 94.4%
79 | 3% | 97.5%
94 | 1% | 98.6%
228 | 1% | 99.7%
TOTAL | 98%

## Thesis plan
| Final report | 2021-09-10
| Oral presentation | 2021-09-08
| Month | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September
| Commencing | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06
| Week number | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Item | Revision & Exams
Identify dataset requirements | bar: 2021-05-10 to 2021-05-31
Plan data collection experiments (channels, sampling rates, sensors) | bar: 2021-05-17 to 2021-06-07
Design data collection rig | bar: 2021-05-24 to 2021-06-14
Source sensing hardware | bar: 2021-06-07 to 2021-06-14
Experiment set up complete | bar: 2021-06-14
Run data collection | bar: 2021-06-14 to 2021-06-21
Implement vital sign detection algorithm | bar: 2021-06-28 to 2021-07-05; 2021-07-26 to 2021-08-02
Train and test algorithm | bar: 2021-07-12; 2021-08-09
Document | bar: 2021-07-19; 2021-08-16
Final report structure agreed | bar: 2021-08-16
Report writing | bar: 2021-07-19 to 2021-09-06
Report draft review | bar: 2021-08-23
Oral presentation | bar: 2021-09-06
Final report Submission | bar: 2021-09-06

## Summary
|  |  |  | Driving behaviour |  |  |  |  | Driver behaviour |  |  |  |  | Driver physiological
| Paper | DDA | DRA | Steering wheel angle | Steering Torque | Throttle positon | Lane position | Vehicle speed | Head tracking | Eye Tracking | Facial expression | Posture | Audio | EEG | EMG | EOG | ECG | PPG | Radar heart rate | Respiration rate
1 | Wollmer (2011) | 1 |  | 1 |  | 1 | 1 |  | 1 | 1
2 | Liang (2014) | 1 |  | 1 |  |  | 1 |  |  | 1
3 | Aksjonov (2019) | 1 |  |  |  |  | 1 | 1
4 | Ding (2019) | 1 | [6 empty] | 1
5 | Zhang (2014) |  | 1 | [10 empty] | 1 | 1 | 1
6 | Tsuchiya (2020) |  | 1 | [15 empty] | 1
7 | Jung (2014) |  | 1 | [13 empty] | 1
8 | Li (2013) |  | 1 | [14 empty] | 1
9 | Yu (2019) |  | 1 | [7 empty] | 1
10 | Gao (2019) |  | 1 | [10 empty] | 1
11 | Fu (2016) |  | 1 | [10 empty] | 1 | 1 |  |  |  |  | 1
12 | Zhou (2021) |  | 1 | 1 | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1
13 | Craye (2016) | 1 | 1 | 1 |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  |  |  | 1
14 | Dua (2019) | 1 | 1 | [5 empty] | 1 | 1 | 1
| TOTALS | 6 | 10 | 4 | 1 | 2 | 3 | 1 | 4 | 4 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 2
| DDA |  |  | 2 | 0 | 1 | 3 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DRA |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 2 | 1 | 2 | 1 | 1 | 2
|  | Driving behaviour |  |  |  |  | Driver behaviour |  |  |  |  | Driver physiological
|  | Steering wheel angle | Steering Torque | Throttle positon | Lane position | Vehicle speed | Head tracking | Eye Tracking | Facial expression | Posture | Audio | EEG | EMG | EOG | ECG | PPG | Radar heart rate | Respiration rate
| DDA | 2 | 0 | 1 | 3 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DRA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 2 | 1 | 2 | 1 | 1 | 2
| Combined | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0

## Sheet4
| Driving behaviour |  |  |  |  | Driver behaviour |  |  |  |  | Driver physiological
| Steering wheel angle | Steering Torque | Throttle positon | Lane position | Vehicle speed | Head tracking | Eye Tracking | Facial expression | Posture | Audio | EEG | EMG | EOG | ECG | PPG | Radar heart rate | Respiration rate
DDA | 2 | 0 | 1 | 3 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DRA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 2 | 1 | 2 | 1 | 1 | 2
Combined | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0